COMP-2025-NVWA: Corrective Action Plan — NVWA Citation Response

| Document ID | COMP-2025-NVWA |
| --- | --- |
| NVWA Citation | NVWA-2025-CIT-04412 |
| Citation Date | 12 June 2025 |
| Response Submitted | 15 July 2025 |
| MCG Contact | Dr. Elena Vasquez, Chief Compliance Officer |
| Status | In Progress — 3 of 5 actions on track |
| Next Inspection | Expected Q1 2026 |

1. Citation Summary

On 12 June 2025, the Netherlands Food and Consumer Product Safety Authority (NVWA) conducted a routine inspection at MCG's Rotterdam Distribution Center (Europaweg 120, 3199 LD Rotterdam). The inspection identified 5 findings:

| Finding | Severity | Description |
| --- | --- | --- |
| F1 | Major | Lot numbers not consistently captured at goods receipt |
| F2 | Major | Unable to complete product trace within 24 hours |
| F3 | Significant | Country of origin missing for 12% of fresh produce |
| F4 | Significant | Sub-tier supplier relationships not documented |
| F5 | Observation | Inconsistent timestamp formats in temperature records |

2. Corrective Action Status

2.1 Action 1: Lot Number Capture (F1)

Target: 100% lot capture for all food products

Deadline: 01 October 2025

Status: 93% complete — On Track

WMS goods receipt forms converted from free-text to structured input with validation. Blank lot numbers now blocked at system level. Remaining 7% are legacy warehouse locations using older handheld scanners that require firmware update (scheduled for October).

2.2 Action 2: Store Receipt Tracking (F2)

Target: 90% lot-level tracking at retail stores

Deadline: 01 March 2026

Status: 78% complete — In Progress

Store POS systems being updated to scan and record lot numbers at receipt. 78% of stores (890 of 1,140) now have the capability. Remaining 250 stores (primarily MCG Express format) require POS hardware upgrade.

2.3 Action 3: Unified Traceability (F2)

Target: Single-query traceability across SAP, WMS, TMS, Salesforce

Deadline: Project CLARITY Phase 1

Status: Business case submitted — Pending CIO approval

This corrective action depends on the implementation of Project CLARITY, which will create a unified data layer connecting all 4 traceability systems. Business case presented to senior leadership on 15 October 2025. CIO review scheduled for 31 October 2025.

2.4 Action 4: Sub-Tier Supplier Mapping (F4)

Target: 80% of food suppliers with documented sub-tier relationships

Deadline: 01 January 2026

Status: 36% complete — At Risk ⚠

|  | This action is at risk. Only 36% of food suppliers have provided sub-tier documentation. Many suppliers cite commercial confidentiality. The Fresh Direct lettuce recall demonstrated the risk of undisclosed sub-tier suppliers. |
| --- | --- |

2.5 Action 5: Country of Origin Compliance (F3)

Target: 100% country of origin for fresh produce

Deadline: 01 November 2025

Status: 88% complete — On Track

Procurement team has updated supplier requirements. 88% of fresh produce SKUs now have validated country of origin. Remaining 12% are sourced from multi-origin suppliers where country varies by shipment — process being developed.

3. Preparation for Q1 2026 Follow-Up

NVWA has indicated a follow-up inspection in Q1 2026. MCG must demonstrate:

1. 100% lot number capture operational

2. Meaningful progress on store-level tracking (target: 90%)

3. Approved plan and timeline for unified traceability

4. Documented progress on sub-tier supplier mapping

5. Complete country of origin compliance

Dr. Elena Vasquez

Chief Compliance Officer

Legal & Compliance Division