Project Qlarity: Business Case for Qlik Platform Implementation

| Document ID | PROJ-CLARITY-2025 |
| --- | --- |
| Version | 2.0 |
| Date | 15 October 2025 |
| Author | Priya Ramanathan, Chief Data Officer |
| Sponsor | Ingrid van der Berg, CEO |
| Status | Pending CIO Approval — Review: 31 October 2025 |
| Investment | $12.4M over 24 months |
| Expected Benefit | $52.7M–$87.9M annually |
| ROI (3-Year, Conservative) | 952% |

1. Executive Summary

Meridian Commerce Group's data quality crisis costs an estimated $127M annually across seven identified problem areas ('The Seven Data Quality Nightmares'). Project Qlarity proposes a $12.4M investment in the Qlik data platform to create a unified, governed, and trusted data foundation. Conservative projections show $52.7M in annual benefits, yielding a 952% 3-year ROI with payback within 4 months of Phase 1 completion.

The urgency is driven by three converging pressures: (1) the NVWA regulatory citation requiring credible corrective action by Q1 2026, (2) escalating operational losses ($2.48M in Q3 2025 spoilage alone), and (3) competitive pressure as peers adopt data-driven supply chain optimization.

2. The Problem: Seven Data Quality Nightmares

| # | Nightmare | Annual Cost | Key Metric | Worst Incident (Q3) |
| --- | --- | --- | --- | --- |
| 1 | Phantom Inventory | $48.0M | IRA: 74% (target 97%) | INC-2025-04872: 847 phantom units from 72hr pipeline failure |
| 2 | Address Data Catastrophe | $3.1M | 4.7% first-delivery failure | $847K FedEx correction surcharges in FY2024 |
| 3 | Product Master Mess | $8.2M | 8,200 SKUs missing weight | Dimensional weight overbilling across all carriers |
| 4 | Silent Pipeline Failures | $12.0M | 4.3-day avg detection | INC-2025-04872: 72hrs undetected at Rotterdam |
| 5 | Timestamp Tower of Babel | $6.5M | 14 TZs, no standards | Ongoing confusion in every cross-system report |
| 6 | Carrier Data Black Hole | $14.8M | 42% missing tracking #s | NinjaVan SG tracking at 71% (target 99%) |
| 7 | Compliance Traceability Gap | $4.2M | 11-day recall trace | RCL-2025-003: €85K recall cost, NVWA citation |

Total Annual Impact: $127.0M (conservative, based on directly attributable and quantified costs)

3. Proposed Solution: Qlik Platform

| Component | Purpose | Addresses Nightmares |
| --- | --- | --- |
| Qlik Talend Cloud — Data Integration | CDC pipelines from SAP, WMS (Oracle + Manhattan), Salesforce, IoT, TMS | #1, #4, #7 |
| Qlik Talend Cloud — Data Quality | Automated profiling, address standardization, supplier dedup, product master harmonization | #2, #3, #6 |
| Qlik Talend Cloud — Data Stewardship | Workflow for resolving data quality issues with SLA tracking and accountability | #1-#7 |
| Qlik Open Lakehouse | Unified Bronze/Silver/Gold data architecture on Apache Iceberg | #1-#7 |
| Qlik Analytics | Interactive dashboards for supply chain, inventory, cold chain, carrier performance | #1, #4, #5, #6 |
| Qlik AutoML | Predictive models for demand forecasting, spoilage risk, delivery SLA prediction | #1, #6 |
| Qlik Answers | Conversational AI over SOPs, policies, contracts — enables warehouse staff to query procedures | Operational efficiency |
| Qlik Discovery Agent | AI agent for automated data exploration and root cause analysis | #1, #4, #6 |

4. Implementation Phases

4.1 Phase 1: Foundation (Months 1-8, $5.2M)

Core data infrastructure and the 4 highest-priority transformation routes:

| Deliverable | Description | Nightmare Addressed |
| --- | --- | --- |
| CDC Pipelines | Real-time CDC from SAP, Oracle WMS, Manhattan WMS, Salesforce | #1, #4 |
| Open Lakehouse (Bronze/Silver) | Apache Iceberg storage with automated ingestion and quality checks | Foundation |
| Timestamp Normalizer | Standardize all timestamps to UTC with source timezone metadata | #5 |
| Inventory Reconciliation | Automated WMS-SAP reconciliation replacing manual daily checks | #1 |
| Carrier Status Normalizer | Multi-language carrier status mapping (DPD, FedEx, NinjaVan, TransFrio) | #6 |
| IoT Telemetry Pipeline | Tive sensor data integration with carrier and product context | #6, spoilage detection |
| Pipeline Health Monitoring | Heartbeat checks, row-count reconciliation, sync lag alerting for all 28 DCs | #4 |
| Qlik Analytics Dashboards (v1) | Inventory accuracy, cold chain monitoring, pipeline health | #1, #4 |

4.2 Phase 2: Analytics & Quality (Months 6-16, $4.8M)

Advanced data quality, remaining transformation routes, and predictive analytics:

- Address Standardization — postal address validation and correction for EU, Americas, APAC (addresses Nightmare #2)

- Product Master Harmonizer — cross-system SKU matching, weight/dimension completion (addresses #3)

- Supplier Identity Resolution — fuzzy matching to create canonical supplier records across SAP, WMS, Salesforce (addresses #3)

- Order Enrichment — end-to-end order tracking from PO to delivery with unified timestamps (#5, #6, #7)

- Enterprise Data Quality Trust Score — automated scoring across all 6 quality dimensions (#1-#7)

- Data Stewardship Workflows — issue routing, SLA tracking, accountability framework

- Qlik AutoML models — demand forecasting (reduce phantom inventory), spoilage risk prediction, delivery SLA prediction

- Gold Tier data products — curated, governed datasets for business consumption

4.3 Phase 3: AI & Conversational (Months 14-24, $2.4M)

AI-powered analytics and conversational access to MCG's data and documents:

- Qlik Answers knowledge base — ingest all SOPs, policies, carrier contracts, training guides, and operational documents for conversational Q&A

- Discovery Agent — automated root cause analysis for anomalies (e.g., auto-detect spoilage correlation with fleet changes)

- MCP Server — enable AI agent integration with MCG's data platform via Model Context Protocol

- Conversational analytics — natural language query for store managers, customer service agents, and operations staff

5. Financial Model

| Benefit Category | Conservative (60%) | Expected (80%) | Optimistic (100%) |
| --- | --- | --- | --- |
| Phantom inventory reduction | $28.8M | $38.4M | $48.0M |
| Carrier cost optimization | $8.9M | $11.8M | $14.8M |
| Pipeline failure prevention | $7.2M | $9.6M | $12.0M |
| Address quality improvement | $1.9M | $2.5M | $3.1M |
| Product master clean-up | $4.9M | $6.6M | $8.2M |
| Compliance risk reduction | $1.0M | $2.0M | $4.2M |
| Total Annual Benefit | $52.7M | $70.9M | $87.9M |

3-Year ROI (Conservative): 952%

Payback Period: < 4 months from Phase 1 completion

NPV (10% discount rate, 3 years): $118.4M

6. Risk Factors

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| CDC performance impact on production SAP | Low | High | Agentless CDC; proven at scale on SAP S/4HANA |
| User adoption of new dashboards | Medium | Medium | Phased rollout with role-based training program |
| Data quality improvement slower than projected | Medium | Medium | Conservative 60% realization used in base financial model |
| Scope creep from 47 source systems | High | Medium | Phase 1 strictly limited to 4 critical source systems |
| NVWA enforcement before Phase 1 completion | Low | High | Interim manual improvements + approved project plan as evidence |

7. Approval Requested

Approval is requested for $12.4M total investment over 24 months, structured as:

- Phase 1: $5.2M — begin Q1 2026 (critical for NVWA compliance and Nightmare #1/#4 remediation)

- Phase 2: $4.8M — begin Q3 2026 (requires Phase 1 foundation)

- Phase 3: $2.4M — begin Q1 2027 (AI capabilities, lower urgency)

Priya Ramanathan

Chief Data Officer

Project Sponsor

Ingrid van der Berg

Chief Executive Officer

Executive Sponsor